## Sheet1
Instructions
Version | 2.0 (2/12/2014) for CPCC
Phase Initiated | High Level Task List for Channel Partner/Distributor
Tool Name | Task Table Template
Description | This document is used to help internally to walk through the tasks needed for implementing eBusiness transactional messages. These are the typical tasks. This is not an exclusive list, each company should review and determine what is needed for their systems and processes.
Doc Type | Shared
Recommended
Reference
Usage | Used to help start a project plan for implementing eBusiness in the Crop Protection segment.
Revisions | Updated for CPCC Project - 2014
New User: | Good starting point for new users
Experienced User: | Modify to add detail and dependent tasks

## Task_Table
ID | Name | Duration | Start | Finish | Notes | Earliest | Latest
1 | Project Planning
2 | Determine Scope of Business Objectives (internal)
3 | Review of Documents from Project Coordinator
4 | Business Use Cases Review (documents)
5 | Develop internal business process diagram
6 | Identify areas where internal business rules need to be defined (Excel Doc)
7 | Distributor Data Requirements Document Complete
8 | Review Data Element Definition (Excel mapping files)
9 | Develop targeted Trading Partners to connect with (list by priority)
10 | Discuss Requirements of Trading Partners (current understanding)
11 | Complete the Roles and Responsibility Form (document)
12 | Additional Project Scope Planning Sessions (if needed)
13 | Complete the Implementation Initiation Form (document)
14 | Complete Technical Data Form
15 | Data Synchonization - Order to Invoice
16 | Determine what format to use for AGIIS synchronization
17 | If subset does not exist: Create a data upload to create an AGIIS subset with the ShipTo demographics (in the AGIIS file format)
18 | If Subset exists: Create a data extract from AGIIS to validate against e-Business System
19 | Validate AGIIS extract to internal database information
20 | Determine gaps or differences from AGIIS
21 | Determine if AGIIS is correct or internal database and correct differences
22 | Complete the Business Data Exchange Form or create document for TP of ShipTo locations(document - or check with TP)
23 | Receive from TP ship from locations, and products from Seller - validate against internal database
24 | Determine gaps or differences from AGIIS and correct differences
25 | Determine Scope of Technical Objectives
26 | Internal Review of Project Materials
27 | Review Technical Requirements
28 | Review Availability of Technical Resources
29 | Review Current Infrastructure / XML Middleware Investments
30 | Infrastructure Upgrade Plan
31 | Develop or review Physical Infrastructure Upgrade/Implementation Plan
32 | Messaging tool evaluation and selection
33 | Server and network evaluation and selection
34 | Logical Infrastucture Upgrade/Implementation Plan (if needed)
35 | Back-end Connection tool evaluation and selection
36 | Develop Planning Document for Infrastructure Upgrades (if needed)
37 | Infrastructure Scope Document Complete
38 | Infrastructure Upgrade Plan Revision
39 | Final Approval of Infrastructure Upgrade Plan
40 | Resource Plan
41 | Develop Initial Resource Plan
42 | Resource Planning Document Complete
43 | Final Approval of Resource Planning Document
44 | XML Middleware Implementation / Upgrade Plan
45 | Develop Implementation Plan for XML Middleware Installation/Configuration
46 | XML Middleware Implementation Plan Complete
47 | XML Middleware Implementation Plan Revision (if necessary)
48 | Final Approval of XML Middleware Implementation Plan
49 | Messaging Design & Infrastructure Implementation
50 | Infrastructure Upgrades (As Needed)
51 | Obtain Internet Connection Upgrades & IP Addresses
52 | Order Application Server and Other Hardware
53 | Receive Server and Other Hardware
54 | Upgrades to Network / Firewall Configuration
55 | Obtain SSL Certificate
56 | XML Middleware Installation / Upgrades (If Needed)
57 | Installation Planning Session
58 | Install and Configure Messaging Engine
59 | Configure and Test Firewall
60 | Complete Successful Test Message to External Server
61 | Complete Successful Test Message with Trading Partner
62 | Document Software/Hardware/Network Configuration
63 | Load SC Transactions, Choreographies, and Sample Connectors
64 | Design of Business System Connectors
65 | Design Connector Architecture
66 | Architecture Document Complete
67 | Connector Design (Per Transaction)
68 | Order Process
69 | Review mapping tool
70 | Create or Revise Mapping Document
71 | Design Custom Connector,Triggers and Alerts
72 | Maps and Connector Design Documents Complete
73 | Invoice
74 | Review mapping tool
75 | Create or Revise Mapping Document
76 | Design Custom Connector & Triggers
77 | Maps and Connector Design Documents Complete
78 | ShipNotice
79 | Review mapping tool
80 | Create or Revise Mapping Document
81 | Design Custom Connector & Triggers
82 | Maps and Connector Design Documents Complete
83 | Development
84 | Project Status Review Meeting
85 | OrderCreate
86 | Develop Collaboration / Orchestration
87 | Develop and/or Modify Maps / Transformations
88 | Develop and/or Modify Business Objects
89 | Develop Custom Connectors
90 | Unit Testing
91 | Connector Components Complete
92 | Update System Documentation
93 | Transaction Documentation Complete
94 | OrderResponse
95 | Develop Collaboration / Orchestration
96 | Develop and/or Modify Maps / Transformations
97 | Develop and/or Modify Business Objects
98 | Develop Custom Connectors
99 | Unit Testing
100 | Connector Components Complete
101 | Update System Documentation
102 | Transaction Documentation Complete
103 | Test Plan Development (Order & Response)
104 | Development of Formal Test Plans with TP
105 | Documentation of Testing Procedures
106 | Creation of Test Data (Outbound)
107 | Documentation for Test Data (Inbound)
108 | Development Completion Checklist
109 | Invoice
110 | Develop Collaboration / Orchestration
111 | Develop and/or Modify Maps / Transformations
112 | Develop and/or Modify Business Objects
113 | Develop Custom Connectors
114 | Unit Testing
115 | Connector Components Complete
116 | Update System Documentation
117 | Transaction Documentation Complete
118 | Test Plan Development (Invoice)
119 | Development of Formal Test Plans with TP
120 | Documentation of Testing Procedures
121 | Creation of Test Data (Outbound)
122 | Documentation for Test Data (Inbound)
123 | Development Completion Checklist
124 | ShipNotice
125 | Develop Collaboration / Orchestration
126 | Develop and/or Modify Maps / Transformations
127 | Develop and/or Modify Business Objects
128 | Develop Custom Connectors
129 | Unit Testing
130 | Connector Components Complete
131 | Update System Documentation
132 | Transaction Documentation Complete
133 | Test Plan Development (ShipNotice)
134 | Development of Formal Test Plans with TP
135 | Documentation of Testing Procedures
136 | Creation of Test Data (Outbound)
137 | Documentation for Test Data (Inbound)
138 | Development Completion Checklist
139 | Testing
140 | Hold Scheduling and Planning Meeting
141 | Review and Update Test Scripts
142 | Prepare Test Data
143 | Test Using Prepared Data
144 | Parallel Testing Until Success Criteria Met
145 | Primary Testing Complete
146 | Performance/Stress Testing (Optional)
147 | Review Test Scenarios
148 | Revise or Develop Testing Scenarios
149 | Prepare Test Data
150 | Conduct Performance/Stress Tests
151 | Develop Test Result Documentation
152 | Develop Remediation Plan (If Needed)
153 | Implement System Changes
154 | Failover / System Failure Testing
155 | Review Error Testing Scenarios
156 | Identify and Document Failure Conditions
157 | Develop Test Scripts
158 | Prepare Test Data
159 | Conduct Failover / Failure Testing
160 | Develop Test Result Documentation
161 | Develop Remediation Plan (If Needed)
162 | Implement System Changes
163 | Production
164 | OrderCreate & OrderResponse
165 | Pre Production
166 | Scheduling Meeting for Trading Partner Testing / Cutover Planning
167 | Testing and Implementation Timeline Document
168 | Develop Contact List for Production
169 | Trading Partner Testing
170 | Contact Trading Partner Testing Team
171 | Review Trading Partner Transaction Standards
172 | Review Test Scripts / Procedures
173 | Test Using Prepared Data
174 | Parallel Testing (if possible)
175 | Production
176 | Cutover Date
177 | Invoice
178 | Pre Production
179 | Scheduling Meeting for Trading Partner Testing / Cutover Planning
180 | Testing and Implementation Timeline Document
181 | Develop Contact List for Production
182 | Trading Partner Testing
183 | Contact Trading Partner Testing Team
184 | Review Trading Partner Transaction Standards
185 | Review Test Scripts / Procedures
186 | Test Using Prepared Data
187 | Parallel Testing (if possible)
188 | Production
189 | Cutover Date
190 | ShipNotice
191 | Pre Production
192 | Scheduling Meeting for Trading Partner Testing / Cutover Planning
193 | Testing and Implementation Timeline Document
194 | Develop Contact List for Production
195 | Trading Partner Testing
196 | Contact Trading Partner Testing Team
197 | Review Trading Partner Transaction Standards
198 | Review Test Scripts / Procedures
199 | Test Using Prepared Data
200 | Parallel Testing (if possible)
201 | Production
202 | Cutover Date
203 | Project Management
204 | Prepare Weekly Status Report
205 | Update Project Plan
206 | Update Project Plan 1
207 | Update Supporting Documentation
208 | Update Supporting Documentation 1
209 | Maintain Issues List
210 | Maintain Issues List 1
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309